## Sheet1
Recruiting Action Plan
*Click here to gain access to PCPS Tools
What | Who | PCPS Tool* | When ** | Status | Notes
Prospecting
Communicate with high school contacts and obtain student list and college attending | Marketing champion or assigned internal champion |  | February
Prepare summer picnic invite for incoming college juniors, seniors and 5th year students and communicate with local universities | Marketing champion or assigned internal champion | Recruiting and Prospecting Guide | May
Conduct summer picnic | Recruiting committee |  | June/July
Assign High School visitations | Recruiting committee |  | Aug/Sept
Conduct High School visits | Everyone (especially Young CPAs group) |  | Sept-Jan |  | (Use the "Start Here Go Places" site and the "Takin' Care of Business" presentation)
Firm Needs Assessment
Read "Assessing Team Resources" | Recruiting committee | Assessing Team Resources | July
Assess firm staffing needs | Recruiting committee | Team Member Competency Assessment Tool | July
Review and revise job qualifications and descriptions | HR Champion | CPA Firm Professional Role Descriptions | July
Evaluate internal promotions and job shifts | HR Champion |  | August
Evaluate upcoming new client needs | Senior Managers/Directors | Team Member Competency Assessment Tool | September
On Campus Recruiting
Read "Recruiting and Prospecting Guide" | HR Champion | Recruiting and Prospecting Guide | August
Read "Interview Tips and Tricks Guide" | HR Champion | Interview Tips and Tricks | August
Coordinate on campus visits with local universities | HR Champion |  | August
Coordinate pre-interview reception with universities | HR Champion |  | August
Attend all university professional nights and career fairs | HR Champion & 1-2 newer professionals |  | Sept-Oct
Selection of On campus interviews based on summer picnic attendees, attendees at meet the professionals and any other firm contact | Recruiting committee |  | October
Create database of candidates | HR Champion | Candidate Database Template | Ongoing
Send Behavioral Based Interview questions to candidates via email or mail. | HR Champion | Interview Questions by Role | 2-5 days before interview
On Campus Recruiting (Continued)
Conduct pre-interview reception | HR Champion & 1-2 newer professionals | PreInterview Reception Script | Night before interview
Conduct on campus interviews | HR Champion & 1 greeter | Intern or Associate Interviews | October
Evaluate all first interview results and recommend for seconds | HR Champion/Recruiting Committee | Candidate Database Template | Oct/Nov
Thank you letters to all 1st Interview Candidates not continuing in the process. | HR Champion/Recruiting Committee | Sample Recruiting Letters and Telephone Scripts | November
Invite all second interview candidates to a social function(sporting event, office reception, etc.) | HR Champion, 1 additional decision maker, 1 newer professional |  | November
Identify top # candidates equivalent to # of positions to fill. (e.g. hiring two, identify top two candidates) | Recruiting committee |  | November
Conduct in office second interviews (see in office interview checklist), interview top # of candidates last and make offer at the end of visit | HR Champion | Sample Offer Letters | November
Thank you letters to the bottom half of second interview candidates not making an offer. Personal calls to top half of candidates not making an offer. | HR Champion | Sample Recruiting Letters and Telephone Scripts | November
Background checks, reference checks and transcript from accepted candidates. | HR Champion | Reference Check Screening | November
Internship
Establish and commit to an internship program | Recruiting committee | Designing an Internship Program | Immediately
Coordinate intern opportunities with local universities | HR Champion |  | September
Interview for tax intern | HR Champion | Intern or Associate Interviews | October
Make intern selection and offer | HR Champion | Sample Offer Letters | November
Interview for summer intern | HR Champion | Intern or Associate Interviews | January
Make intern selection and offer | HR Champion | Sample Offer Letters | February
Experience Hire Recruiting
Establish level is necessary to fill. Re-evaulate internal needs and determine if position can be filled internally | Recruiting committee
Review firm alumni list to determine potential for a re-hire | HR Champion
Review candidate database from the last few years' on campus program to source directly to next tier of recruits not hired. | HR Champion
Place ad in local paper, monster and other recruiting sources | HR Champion | Recruiting and Prospecting Guide
Engage current team members to assist in search through referral fee and local functions | HR Champion
Conduct interviews | HR Champion
**- Dates provided are suggested time frames only. Each firm should check with the university career centers and local market trends for exact timing of all recruiting functions.
DISCLAIMER: This publication has not been approved, disapproved or otherwise acted upon by any senior technical committees of, and does not represent an official position of, the American Institute of Certified Public Accountants. It is distributed with the understanding that the contributing authors and editors, and the publisher, are not rendering legal, accounting, or other professional services in this publication. If legal advice or other expert assistance is required, the services of a competent professional should be sought.